## Sprint#0
#Sno | Deliverables #Sprint-0 | Status | Action Owner | Remarks | Target date
1 | Environment Setup - UI | 100% | Vivek/Seenu | Dependency: DB access issue and API access issue | 2021-11-08
2 | Environment Setup - Backend (API) | 100% | ChemTreat | Dependency: DB access issue and API access issue
3 | Environment Setup - DB | Done | Gaurav | Dependency: DB access issue
4 | Environment Access - DB Dev Instance | Done | John/Tim/TCS team | Requested customer about the DB access.(open for the last 3 weeks), which will delay further sprint implementation and delivery.
5 | Environment Access - DB UAT Instance | ToDo | John
6 | Environment Access - DB Prod Instance | Done | John/Tim/TCS team | Requested customer about the DB access.(open for the last 3 weeks), which will delay further sprint implementation and delivery.
7 | GitHub Repository Code Server access | Done | John | Team is good to access the code repository
8 | High Level Architecture | In progress | Team
9 | Existing code analysis and understanding | In progress | Team | Req. working deployment build script KT, reasons to know about the 3rd party chart library customization.
10 | Need to verify the Dev instance code is in sync with the UAT and Master branches | Done | Team | Done. (Andres has created both Dev and Test branches)
11 | CT Vista Plus Dev Instance Access | Done | John
12 | CT Vista Plus UAT Instance Access | ToDo | John | Not required now
13 | CT Vista Plus Prod Instance Access | Done | John
14 | Deployment server (Unix) - Dev Access | Done | John
15 | Deployment server (Unix) - UAT Access | ToDo | John | Not required now
16 | Deployment server (Unix) - Prod Access | Done | John
17 | Understanding the requirements | In progress | Team | Will continue this task till end of all the sprints.
18 | Create Task List - UI | Done | Sneha
19 | Create Task List - Backend (API) | Done | Srinivas/Raj/Dev
20 | Create Task List - DB | Done | Gaurav
21 | Existing code/framework walk through, build/deployment scripts | ToDo | ChemTreat

## Sprint Backlogs
| Sprint# | Start date | End date |  |  |  | Remarks
| Sprint#0 | 27 Sep'21 | 11 Oct'21 |  |  |  | Doing Sprint#0
| Sprint#1 | 12 Oct'21 | 2 Nov'21 |  |  |  | Done Spring#0
| Sprint#2 | 3 Nov'21 | 23 Nov'21 |  |  |  | Doing Sprint#1
| Sprint#3 | 24 Nov'21 | 12 Dec'21
Sprint#4
Sprint#5
| Sprint#6 | [5 empty] | Stage Deployment/UAT/Prod Deployment
#Sno | Tasks from Customer Deck | Tasks from TCS Proposal Deck | Web API-Tasks | Web API-Sub-tasks | Sub-tasks | Web-API Tasks-Questions | Angular-Tasks | Status | Action Owner | Remarks | Target date | From Sprint
1 | Scatter plot of two parameters | Scatter Plot Charts | 1. Create a microservice to extract JSON data for the scatter charts from the DB |  |  |  | 1. Create a tab for Scatter charts. 2.Enable provision for user to select two parameters one maps to x axis and other maps to y axis. 3. Refine scatter plot based on load range and date range filters. 4. Provide the script for Rsquared values and display it on the chart/graph area. | ToDo | Seenu |  | 17 Nov'21 | Sprint#1
2 |  | Data point counter |  |  |  |  | 1. Extract the records size paramter from api response and assign it to field. | Testing Complete | Vivek |  | 9 Nov'21 or 10 Nov'21 | Sprint#1
3 | Compare up to four parameters in a single chart - advanced charts page | Allowing 8 chart selection - advanced charts |  |  |  |  | 1. Write the validation script for limiting 8 chart selection - advanced charts | Testing Complete | Vivek |  | 9 Nov'21 or 10 Nov'21 | Sprint#1
4 | Add multivariate charts in a report - advanced charts page | Multi variant chart plotting - advanced charts |  |  |  |  | 1. Identify chart plotting library 2. Make necessary configuration changes 3. Implement the multi parameter chart plotting | Testing Complete | Vivek |  |  | Sprint#1
5 | Filter outliers from KPI charts / Custom charts | Modification of Date and Load range in reports page |  |  |  |  | 1. Set the necessary flag to make both the fields editable in reports page 2. Plot the chart according to values set in the date as well as load range. | In progress | Seenu |  | 9/11 or 10/11 | Sprint#1
6 |  | Chart Loading Indicator |  |  |  |  | 1. Provide the loading indicater - advanced charts page | Testinng complete | Vivek |  | 9/11 or 10/11 | Sprint#1
7 | Add new parameters for a condenser for monitoring - for trending in custom and advanced charts page | Custom Parameters - Create customer parameter in the Historian tag page |  |  |  |  | 1. Developing UI for users to add custom parameters dynamically 2. Sending those inputs as parameters through API | In progress | Vivek |  |  | Sprint#2
8 | Save selected charts in custom charts page for next work session | Favourite Charts |  |  |  |  | Provide the link for favourite charts. Save and load the user saved favourite charts groups and the associated charts |  | Vivek/Seenu |  |  | Sprint#2
9 | Filter outliers from KPI charts / Custom charts / Create upper control limits with ability to send alerts | Y-Axis limits for charts |  |  |  |  | 1. Develop the UI component for the Y-Axis limit value from KPI, Custom charts. 2. develop script for the alerting when the chart goes beyond the upper control limits |  | Vivek/Seenu |  |  | Sprint#2
10 |  | Metric Preferences |  |  |  |  | Enable to metric preferences from angular script, send the user selected metric flag from the web API call. |  | Vivek/Seenu |  |  | Sprint#2
11 | Add new parameters for a condenser for monitoring - for trending in custom and advanced charts page | API changes for the custom parameters | 1. Update existing Historian service API 2. Analyze and process the historian tab JSON data 3. Update the table along with custom parameters 4. Return the response to the UI | 1A. Work with UI team and get new JSON format for custom parameter handling. 2A,3A,4A. Process the JSON format, insert custom parameters/update the values for the existing parameters into the table and return the flag to UI. |  |  |  | In progress | Dev |  | 18 Nov'21 | Sprint#1
12 | Save selected charts in custom charts page for next work session | API changes for the Favourite charts | 1. Prepare the JSON request format 2. Create new table 3. Create web API 4. Persist the data into the table 5. Update UI about save status 6. Load the favorite chart data 7. Delete the favorite charts | 1A. Work with UI team and get the request JSON format. 2A. Provide Details to DB team and request to create table. 3A. Create model class, add request parameters to it 3B. Create model repository and queries. 3C. Create model DTO. 4A. Write a function to insert the data into the DB table and return the response flag. 5A. Map the response flag to UI object | 1. JSON format needs to be structured based on data paramters. 2. Handling of JSON data to process request and response. 3. Create a table with assetId, paramId, lower and upperlimit values and other relevant columns. 4.Need to create a web API to get the JSON data from DB. 5. Need to create a web API to store the JSON request body to DB which is received from UI. |  | 1. add the charts to favorites (add to favorites icon/button) 2. provide crud operations in favorites chart listing page. (checkboxes with add(+)/remove (-)) | Testing complete | Yuga |  | 9 Nov'21 | Sprint#1
13 | Filter outliers from KPI charts / Custom charts | API changes for the Y-Axis limits | 1. Prepare the JSON request format 2. Create new table 3. Modify the web API, implement the new save function and call from the called web API 4. Persist the data into the table 5. Update UI about save status | 1A. Work with UI team and get the request JSON format. 2A. Provide Details to DB team and request to create table. 3A. Create model class, add request parameters to it 3B. Create model repository and queries. 3C. Create model DTO. 4A. Write a function to insert the data into the DB table and return the response flag. 5A. Map the response flag to UI object | 1. JSON format needs to be structured based on data paramters. 2. Handling of JSON data to process request and response. 3. Create a table with assetId, paramId, lower and upperlimit values and other relevant columns. 4. Need to create a web APIs to process and send this JSON request to persist in DB. 5. Query logic has to be decided. | 1.If different limits are going to be set by different users, Which limit has to be persisted? or How persistence of limit has to be handled?. 2. Currently persistance of paramter limits is not happening in Advanced charts |  | Modification suggested | Raj | Asked to keep one get API for loading data from custom, kpi and advanced charts? | 9 Nov'21 | Sprint#1
14 | Display units as per metrics system selected in user profile | API changes for the metrics | 1. Access the user preference table from user preference API 2. Based on response user preference API set the global flag and apply necessary metric changes accross all charts | 1. Uom metric conversion function to be created and integrated with existing getcharts api- completed 2. Uom metric conversion function to be integrated with existing y axis limits api- completed 3. Min, Max, Lower and Upper limits got from y axis requests under metric units to be processed to standard units and stored in db - inprogress 4. Display name string to be processed according to metric flag- inprogress |  | 1. Currently language preference changes are made only to navigation text. 2. Currently metric preference changes are not getting reflected in charts. 3.Which API is fired?What link is missing between Ctvista navigation bar and condenser tool? |  | In progress | Raj |  | 17 Nov'21 | Sprint#1
15 | Display content in the app in the language set in user profile - Need to support English, French, Portuguese and Spanish. | API to return the language and metric supported | 1. Access the user preference table from user preference API 2. Based on response user preference API set the global flag and apply necessary language and metric changes |  |  |  |  | ToDo | Vivek/Seenu |  |  | Sprint#1
16 | 1. Email notification for data upload 2. Data upload activity log 3. Removal of non-empty cells | API Changes for data uploads, security scans | 1. Upload issue fix - Completed 2. Email notification on upload success or failure - testing pending 3. Alerting on GUI on upload success of failure - Implementation pending |  |  |  |  | 85% complete | Yuga/Raj |  |  | Sprint#2
17 |  | Selection and display mismatch of charts. - Alert as well as mark the outer lines to red when chart goes beyond the upper/lower limit - |  |  |  |  | write the scipt to verify the upper/lower limits 1) alert the meaningful message. 2) Show the chart outer lines to red | ToDo | Vivek/Seenuvasan |  |  | Sprint#3
18 |  | Plot averaged, summed values of parameters - Slides #4 & #5 & #6 - for W to AN column parameters - applicable for custom, reports, advanced charts page | 1. Make the changes in the existing DTO 2. Modify the existing web api function 3. Verify the data persistence in the table |  |  |  |  | In progress | Yuga |  | 17 Niv'21 | Sprint#2
19 |  | API Changes for Internationalization | [9 empty] | Sprint#2
20 |  | API Changes for User preferences | [9 empty] | Sprint#2
21 |  | API Documentation updates | [9 empty] | Sprint#2
22 | Display content in the app in the language set in user profile - Need to support English, French, Portuguese and Spanish. | Internationalization | [9 empty] | Sprint#3
23 |  | Data uploads from website | [9 empty] | Sprint#3
24 |  | Documentation updates | [9 empty] | Sprint#3
25 |  | API Support | [9 empty] | Sprint#3
26 | Resize uploaded image in rich text editor | Check with customer